## CARES Act Progress Report
[Choose Board of Elections from Dropdown List]
Directive Requirement | Due Date | Progress: July 2020 | Progress: August 2020 | Progress: September 2020 | Progress: October 2020 | Progress: November 2020 | Progress: December 2020 | Comments
Return Signed CARES Act Grant Agreement | 2020-07-13 |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | County IT
Submit CARES Spending Plan to SOS Office | 2020-07-27 |  | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | County Maintenance
Ballot Quantities - All Counties | 2020-09-15 | [7 empty] | Complete
Ballot Quantities: Optical Scan Counties - Pre-Printed Stock | 2020-09-18
Ballot Quantities: Optical Scan Counties - On-Demand Ballots | 2020-09-18
Ballot Quantities: Direct Recording Election (DRE) Voting Machine Counties | 2020-09-18
Staffing | 2020-08-31 | [7 empty] | In Process
Central Count Equipment | 2020-09-15 | [7 empty] | Contractor/Vendor
Personal Protective Equipment | 2020-10-05
Cleaning Supplies | 2020-10-23 | [7 empty] | Ohio Secretary of State Office
Mailing Equipment | 2020-09-15
Precinct Election Official Recruitment | 2020-10-02 | [7 empty] | Yes
Precinct Election Official Training | 2020-10-15 | [7 empty] | No
Paper Pollbook Backups | 2020-10-20 | [7 empty] | Not Applicable
Printed Materials | 2020-10-23
Miscellaneous | 2020-10-23
Polling Place Requirements | 2020-09-18 | [7 empty] | Not Started
Voter Assistance in Senior Living and Health Care Facilities | 2020-08-31
Curbside Voting and Health Screenings | 2020-08-31 | [7 empty] | Board of Elections
Curing Absentee Ballot Applications | 2020-10-31
Curing Absentee Ballots | 2020-11-13 | [7 empty] | Board IT
Board
Director

## Example Information
[Choose Board of Elections from Dropdown List]
Directive Requirement | Due Date | Progress: July 2020 | Progress: August 2020 | Progress: September 2020 | Progress: October 2020 | Progress: November 2020 | Progress: December 2020 | Comments
Return Signed CARES Act Grant Agreement | 2020-07-13 | Returned Grant agreement to SOS Office on July 10 | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | County IT
Submit CARES Spending Plan to SOS Office | 2020-07-27 | Submitted CARES spending plan to the SOS Office July 24. | Not Applicable | Not Applicable | Not Applicable | Not Applicable | Not Applicable |  | County Maintenance
Ballot Quantities - All Counties | 2020-09-15 | Contacted Vendor and obtained quotes. Ordered ballot stock | Placed initial order with vendor. Received Ballot stock | Finalized ballot and received initial order from vendor. Tested the ballots | Placed final ballot order and received and tested ballots. | Provided ballots to polling locations | Not Applicable |  | Complete
Ballot Quantities: Optical Scan Counties - Pre-Printed Stock | 2020-09-18
Ballot Quantities: Optical Scan Counties - On-Demand Ballots | 2020-09-18
Ballot Quantities: Direct Recording Election (DRE) Voting Machine Counties | 2020-09-18
Staffing | 2020-08-31 | Created staffing plan for expected turnout. | [6 empty] | In Process
Central Count Equipment | 2020-09-15 | Contacted vendor and obtained quotes. | Ordered equipment | Received and tested equipment | Used equipment | Used equipment | Returned rented equipment |  | Contractor/Vendor
Personal Protective Equipment | 2020-10-05 | Created allocation based on polling locations and expected increased turn out. | Begin sourcing equipment based on allocation plan.
Cleaning Supplies | 2020-10-23 | Created allocation based on polling locations and expected increased turn out. | Begin sourcing equipment based on allocation plan. | [5 empty] | Ohio Secretary of State Office
Mailing Equipment | 2020-09-15 | Contacted vendor and obtained quotes. | Ordered equipment | Received and tested equipment | Used equipment | Used equipment | Returned rented equipment
Precinct Election Official Recruitment | 2020-10-02 | Sent survey to all past PEOs and everyone who has ever expressed interest. | Contacted PEOS | Recruited back up PEOs | Recruited back up PEOs |  |  |  | Yes
Precinct Election Official Training | 2020-10-15 | Devised PEO training plan | Scheduled in person PEO training | Trained PEOs | Trained PEOs | Not Applicable | Not Applicable |  | No
Paper Pollbook Backups | 2020-10-20 | Determined number needed based on number of ePollbooks. | Contacted vendor and obtained quotes. | Placed order | Received pollbooks and spot checked voters |  |  |  | Not Applicable
Printed Materials | 2020-10-23 | Drafted plan | Drafted documents and obtained quotes | Ordered materials | Received materials | Distributed to the locations | Not Applicable
Miscellaneous | 2020-10-23 | Determined additional needs and contacted the SOS office
Polling Place Requirements | 2020-09-18 | Evaluated current polling locations to ensure they are usable for November | [6 empty] | Not Started
Voter Assistance in Senior Living and Health Care Facilities | 2020-08-31 | Contacted Senior Living and Healthcare facilities | Established plan to vote voters at Senior Living and Healthcare facilities | Communicated plan and scheduled times to vote voters at Senior Living and Healthcare facilities | Voted voters at Senior Living and Healthcare facilities | Voted voters at Senior Living and Healthcare facilities | Not Applicable
Curbside Voting and Health Screenings | 2020-08-31 | Met with department of heath to discuss guidelines | Established plan for curbside voting and sent to Health department for input/approval | [5 empty] | Board of Elections
Board
Director

## Source Lists (hidden)
[Choose Board of Elections from Dropdown List] | Not Started | Board IT
Adams County Board of Elections | In Progress | County IT
Allen County Board of Elections | Complete | Vendor
Ashland County Board of Elections |  | Secretary of State's Office
Ashtabula County Board of Elections
Athens County Board of Elections
Auglaize County Board of Elections
Belmont County Board of Elections
Brown County Board of Elections
Butler County Board of Elections
Carroll County Board of Elections
Champaign County Board of Elections
Clark County Board of Elections
Clermont County Board of Elections
Clinton County Board of Elections
Columbiana County Board of Elections
Coshocton County Board of Elections
Crawford County Board of Elections
Cuyahoga County Board of Elections
Darke County Board of Elections
Defiance County Board of Elections
Delaware County Board of Elections
Erie County Board of Elections
Fairfield County Board of Elections
Fayette County Board of Elections
Franklin County Board of Elections
Fulton County Board of Elections
Gallia County Board of Elections
Geauga County Board of Elections
Greene County Board of Elections
Guernsey County Board of Elections
Hamilton County Board of Elections
Hancock County Board of Elections
Hardin County Board of Elections
Harrison County Board of Elections
Henry County Board of Elections
Highland County Board of Elections
Hocking County Board of Elections
Holmes County Board of Elections
Huron County Board of Elections
Jackson County Board of Elections
Jefferson County Board of Elections
Knox County Board of Elections
Lake County Board of Elections
Lawrence County Board of Elections
Licking County Board of Elections
Logan County Board of Elections
Lorain County Board of Elections
Lucas County Board of Elections
Madison County Board of Elections
Mahoning County Board of Elections
Marion County Board of Elections
Medina County Board of Elections
Meigs County Board of Elections
Mercer County Board of Elections
Miami County Board of Elections
Monroe County Board of Elections
Montgomery County Board of Elections
Morgan County Board of Elections
Morrow County Board of Elections
Muskingum County Board of Elections
Noble County Board of Elections
Ottawa County Board of Elections
Paulding County Board of Elections
Perry County Board of Elections
Pickaway County Board of Elections
Pike County Board of Elections
Portage County Board of Elections
Preble County Board of Elections
Putnam County Board of Elections
Richland County Board of Elections
Ross County Board of Elections
Sandusky County Board of Elections
Scioto County Board of Elections
Seneca County Board of Elections
Shelby County Board of Elections
Stark County Board of Elections
Summit County Board of Elections
Trumbull County Board of Elections
Tuscarawas County Board of Elections
Union County Board of Elections
Vanwert County Board of Elections
Vinton County Board of Elections
Warren County Board of Elections
Washington County Board of Elections
Wayne County Board of Elections
Williams County Board of Elections
Wood County Board of Elections
Wyandot County Board of Elections